## WBS Dictionary
WBS Code | Level | Element Name | Deliverable / Scope | Acceptance Criteria
1.0 | 1 | Drone V1 Air Vehicle Program | Entire program scope | Program baseline approved
1.1 | 2 | Program Management | Roll-up: kickoff, baseline sign-off, customer acceptance
1.1.1 | 3 | Program Kickoff and Planning | Kickoff minutes, initial schedule baseline | WBS and schedule approved by PM and customer rep
1.1.2 | 3 | Production Baseline Sign-off | Production spec, post-flight-test | Signed by chief engineer
1.1.3 | 3 | Customer Acceptance | Formal pre-shipment review | Signed customer acceptance letter
1.2 | 2 | Systems Engineering | Roll-up: air vehicle design
1.2.1 | 3 | Air Vehicle Design | Design package: drawings, BOM | Design freeze approved, BOM released to procurement
1.3 | 2 | Air Vehicle Assembly (Prime Mission Product) | Roll-up: frame, harness, layup, final assembly
1.3.1 | 3 | Frame Fabrication | Fabricated airframe structure | Passes dimensional inspection
1.3.2 | 3 | Wire Harness Install | Harness installed per design | Continuity / point-to-point test passed
1.3.3 | 3 | Layup and Assembly | Composite layup, structural assembly | Passes visual and NDT inspection
1.3.4 | 3 | Final Assembly and Checkout | Fully assembled, powered-on prototype | Power-on self-test passes, no open discrepancies
1.4 | 2 | Peculiar Support Equipment | Roll-up: production line and tooling
1.4.1 | 3 | Production Line and Tooling | Fixtures and tooling for build | Line validated with first-article fit check
1.5 | 2 | Materiel and Procured Components | Roll-up: procured components
1.5.1 | 3 | Procured Components | Motors, frame stock, electronics, battery | Incoming inspection passed, staged for build
1.6 | 2 | System Test and Evaluation | Roll-up: flight test
1.6.1 | 3 | Flight Test | First flight of assembled prototype | Test card complete, no critical anomalies
1.7 | 2 | Operational and Site Activation | Roll-up: first article delivery
1.7.1 | 3 | First Article Delivery | First unit shipped | Shipment docs complete, customer receipt confirmed